## Task Board
No | Story | Definition of Done | Estimated hours | ü | Hours | Tasks
| Planned Points: |  | 36 |  | 10 | Total hours spent
| Gained Points: |  | 6
| Implement functionality when a person enters room | Get data about the person who enters in the room Store data in the DB | 17 |  |  | Brainstorm about the whole feature | Get Bluetooth MAC Address and RSS | Save data in a "History" table | Create VisitorData table
|  |  |  | - | 6 | 4 | 2
[6 empty] | GD + ZK | GD | GD | GD
| Implement functionality when a person leaves room | Get data about the person who leaves the room Store data in the DB | 13 |  |  | Brainstorm about the feature | Detect when a person leaves | Save data in the "History" table
|  |  |  | - | 0
| Implement live charts | Temp and humidity charts to be shown on the UI | 6 | ü |  | Get and show humidity on a chart | Get and show temperature on a chart
|  |  |  | 0.67 | 4 | 2 | 2
[6 empty] | GD | GD
| Miscellaneous Tasks (not in any story, no points gained) |  |  |  |  | Create taskboard excel sheet
1
ZK
Sprint goal: Implement entering in the room functionality
Demo:

## Burndown
| 2017-01-01 | 2017-01-02 | 2017-01-03 | 2017-01-06 | 2017-01-07 | 2017-01-08 | 2017-01-09 | 2017-01-10 | 2017-01-13 | 2017-01-14
| Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue
Total Points | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 |  | Planned stories:
Remaining Points | [11 empty] | Finished stories:
Ideal | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0 | 4