## Task Board
No | Story | Definition of Done | Points | ü | Hours | Tasks
| Planned Points: |  | 68 |  | 40 | Total hours spent
| Gained Points: |  | 42
| Implement functionality when a person enters room | Take photo only when someone gets close to the room | 12 | ü |  | Attach RGB LED | Solve "leaving the room" issue
|  |  |  | 1 | 12 | 10 | 2
[6 empty] | FU + GD | FU + GD
| Create statistics | 1. Temp and humidity 2. People tracking | 18 | ü |  | Create statistics about humidity | Create statistics about temperature | Create statistics about people | UI
|  |  |  | 0.61 | 11 | 2 | 1 | 2 | 6
| Create documentation and put everything together | Create a document containing information about hardware and software | 18 |  |  | Create Component Diagram | Create Use case Diagrams | Create Data flow Diagram | Create document about hardware and soft | Create Readme/HowTo files
|  |  |  | - | 0
| Create final presentation | Create final presentation containing diagrams and features about the project | 12 | ü |  | Create Architecture diagram | Create presentation
|  |  |  | 1.42 | 17 | 5 | 12
| Miscellaneous Tasks (not in any story, no points gained) |  | 8 |  |  | Reviews and other unexpected issues
2
Sprint goal: Get the functionalities done and final presentation.
Demo: 26.07.19

## Burndown
| 2017-01-01 | 2017-01-02 | 2017-01-03 | 2017-01-06 | 2017-01-07 | 2017-01-08 | 2017-01-09 | 2017-01-10 | 2017-01-13 | 2017-01-14
| Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue
Total Points | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 |  | Planned stories:
Remaining Points | [11 empty] | Finished stories:
Ideal | 68 | 60.4444 | 52.8889 | 45.3333 | 37.7778 | 30.2222 | 22.6667 | 15.1111 | 7.5556 | -8.8818e-15 | 7.5556